## Task_Log
Tasks | Due Date | Time Block | What I need to remember or should do | Vital Results | Why I need to do it | Status | Memo
1. Read the task requirements and dataset | Monday 04 Dec | 30 mins | a. audience: the academic module leader and other teaching staff (non-technical); b. prepared empty or initial designed documents include Task Log, Power BI document, Presentation. | a. Download the task in a named folder and dataset in 'raw' folder; b. Create an initial planned task log (it is adjusted iteratively) | Identify the questions for the task, prepare the dataset on-premise | Finished | Final Documents include 1. Task Log, 2. Presentation, 3. Power BI document, 4. Raw Data, 5. Cleansed Data, 6. Transformation Code
2. Check implemented technology, including Power BI add-in for Power Point and Power BI service | Monday 04 Dec | 10 mins | a. Check Power BI service for share function; b. Add Power BI add-in for Power Point | set up all functions work well | Make sure the following steps smooth | Finished
3. Use Excel to check each table for understanding columns and categories inside, find the required metrics as the task mentioned | Tuesday 05 Dec | 2 hours | a. Identify primary key and the relationship between each table; b. Double check data quality, including duplicate values, null values and so on. | Utilise filter and pivot table to put summarised information and data features on one page, see Summary_of_Dataset(Only BBB) | Explore the dataset to understand the meaning of each column | Finished | Data Validation: 1. courses.csv Analyse the B and J presentations separately as the structures may differ; 2. assessments.csv The sum of all other assessments is 100%; 3. vle.csv week_from and week_to columns have many blanks; 4. studentInfo.csv id_student has duplicate values as some students attended more than one presentation, and the ratio of gender is different in different modules; 5. studentRegistration.csv date_registration has blanks; values in the date_unregistration mean Withdrawn; 6. studentAssessment.csv use VLOOKUP to add code_module column to filter BBB, score has blanks; 7. studentVle.csv the table is very big, for some records, the only difference is sum_click
4. Import the prepared dataset into Power BI desktop, double check the data quality, build the relationship for data modelling | Tuesday 05 Dec | 30 mins | a. Remove unneeded records like other modules and blanks for vle.csv; b. Summarise total number of records; c. Import tables into the Power BI desktop; d. Double-check data and build relationship | a. Prepared cleansed data folder and Python code folder; b. 7 Cleansed Tables (parquet) are imported in the Power BI; c. Create a summarised table for the cleansed tables (Changes_of_Cleansed_Dataset); d. Use Data Preview in Power Query Editor to double check data; | 1. make sure the raw data would not be changed; 2. parquet file includes the data type and small for Power BI | Finished | Data Cleansing: 1. courses.csv keep module BBB; 2. assessments.csv keep module BBB; 3. vle.csv keep module BBB and valid week_from, week_to (remove blanks); 4. studentInfo.csv keep module BBB; 5. studentRegistration.csv keep module BBB; 6. studentAssessment.csv merge() adds code_module from assessments.csv, then keep module BBB; 7. studentVle.csv Python filters module BBB and aggragates sum_clicks together for the same code_module, same code_presentation, same id_student, same id_site and same date (reason 1: can not distinguish records which are only different in sum_click; reason 2: save memory)
5. Design how many pages in the PowerPoint and Power BI, and the topics of each page | Thurs 07 Dec | 15 mins | a. An introduction to module BBB 1. Presentation Types, Weightings of Assessments, VLE material b. Student Persona 1. how many students registered for module BBB, 2. how many students registered for each presentation, 3. the distribution of age, region, education c. Results 1. The distribution of results, 2. The trend of score distribution, d. Relationship 1. Percentage of scores below 40, 2. The differences among assessments and presentations | Handwritten design | 1. Give context for background information; 2. Focus on the key metrics, results, and weighting to solve the question; 3. Dive into data and show relationships | Finished
6. Choose the appropriate visuals and put the data in the right place | Thurs 07 Dec | 1.5 hours | visuals title Heading 3, Calibri 14, Bold Text Calibri 16 | Four pages: 1. Overview of module BBB; 2. Student Persona; 3. Overview of Final Results; 4. Relationship | Make sure: No confusion Clear Explanation Correct Number Same Theme | Finished
7. Finish the PowerPoint Slides and make sure the logic is clear and evidence is strong enough for conclusions | Thurs 07 Dec | 15 mins | a. Contents b. Inserted PowerBI reports c. Possible indicators d. Do not forget references | Well Prepared Presentation |  | Finished
8. Put documents in one folder and name them clearly, upload them in the designated folder | Friday 08 Dec | 30 mins | Read the task again to check there is nothing missed | Upload |  | Finished

## Summary_of_Dataset_(Only BBB)
Table Name | Columns (highlight primary and foreign keys) | Simple Summary (filter: BBB) | Memo
courses.csv | code_module
code_presentation
module_presentation_length
assessments.csv | code_module
code_presentation
id_assessment
assessment_type
date
weight
vle.csv | id_site
code_module
code_presentation
activity_type
week_from
week_to
studentInfo.csv | code_module
code_presentation
id_student
gender
region
highest_education
imd_band
age_band
num_of_prev_attempts
studied_credits
disability
final_result
studentRegistration.csv | code_module
code_presentation
id_student
date_registration
date_unregistration
studnetAssessment.csv | code_module (added)
id_assessment
id_student
date_submitted
is_banked
score
studentVle.csv | code_module
code_presentation
id_student
id_site
date
sum_click

## Changes_of_Cleansed_Dataset
Table Name | The number of records (Before) | New Table Name | The number of records (After) | Memo
courses.csv | 22 | courses_BBB.csv | 4
assessments.csv | 206 | assessments_BBB.csv | 42
vle.csv | 6364 | vle_BBB.csv | 186
studentInfo.csv | 32593 | studentInfo_BBB.csv | 7909
studentRegistration.csv | 32593 | studentRegistration_BBB.csv | 7909 | 9 Null Values in date_registration: id 630346 did not register and unregister; id 57369, 342678, 582496, 607646, 614270, 2409808, 2439442, 694001 only unregistered
studentAssesment.csv | 173912 | studentAssessment_BBB.csv | 43032 | 53 Null Values in score
studentVle.csv | 10655280 | studentVle_BBB_aggregate.csv | 1139085